## excel
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Edgar Alexander Aguilar BolaÃ±os
Start Date | abr 18, 2017 07:47:51 AM
Completion Date | abr 19, 2017 12:47:24 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | To Date
Size/Hour | 32.7 | 19.5 | 31.3
Planned Time | 0.31389 |  | 1899-12-31 16:15
Actual Time |  | 0.29097 | 1899-12-31 19:26
CPI (Cost-Performance Index) |  |  | 0.93
% Reuse | 0% | 0% | 5.04%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 17.1 | 7.35 | 16.2
Total Defects/KLOC or equivalent | 34.3 | 29.4 | 33.8
Yield % | 50% | 75% | 52.2%
Code Review Rate | 1154 | 816 | 1134
% Appraisal COQ | 3.84% | 4.53% | 3.95%
% Failure COQ | 15.5% | 5.97% | 14%
COQ A/F Ratio | 0.25 | 0.76 | 0.28
PQI | 0 | 0.02 | 0.01
Program Size
| Plan | Actual | To Date
Base (B) | 303 | 303 | 645
Deleted (D) | 0 | 0 | 2
Modified (M) | 0 | 0 | 6
Added (A) | 247 | 136 | 1355
Reused (R) | 0 | 0 | 97
Added and Modified (A+M) | 247 | 136 | 1361
Total Size (T) | 550 | 439 | 1925
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 217 | 272 | 1481
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | To Date | To Date %
Planning | 0.072917 | 0.045139 | 0.39653 | 21.9%
Design | 0.045833 | 0.12917 | 0.35 | 19.3%
Design Review | 0.0034722 | 0.00625 | 0.021528 | 1.19%
Code | 0.10278 | 0.061111 | 0.55694 | 30.8%
Code Review | 0.0090278 | 0.0069444 | 0.05 | 2.76%
Compile | 0 | 0.00069444 | 0.0020833 | 0.12%
Test | 0.048611 | 0.016667 | 0.25069 | 13.9%
Postmortem | 0.032639 | 0.025 | 0.18194 | 10.1%
Total | 0.31389 | 0.29097 | 1899-12-31 19:26
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | To Date | To Date %
Before Development | 0 | 0 | 0 | 0%
Planning | 0.4 | 0 | 2 | 4.35%
Design | 2.22 | 2 | 13 | 28.3%
Design Review | 0 | 0 | 0 | 0%
Code | 5.84 | 2 | 31 | 67.4%
Code Review | 0 | 0 | 0 | 0%
Compile | 0 | 0 | 0 | 0%
Test | 0 | 0 | 0 | 0%
Total | 8.46 | 4 | 46
Defects Removed
| Plan | Actual | To Date | To Date %
Planning | 0 | 0 | 0 | 0%
Design | 0.2 | 0 | 1 | 2.17%
Design Review | 0 | 1 | 1 | 2.17%
Code | 2.22 | 1 | 12 | 26.1%
Code Review | 1.81 | 1 | 10 | 21.7%
Compile | 0 | 0 | 0 | 0%
Test | 4.23 | 1 | 22 | 47.8%
Total | 8.46 | 4 | 46
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | To Date
Defects/Hour - Design Review | 0 | 6.67 | 1.94
Defects/Hour - Code Review | 8.48 | 6 | 8.33
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 3.64 | 2.5 | 3.66
DRL (DLDR/UT) | 0 | 2.67 | 0.53
DRL (Code Review/UT) | 2.33 | 2.4 | 2.28
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Report generated at 01:37 PM on 19/04/2017